## Slide 1: WP4 Activities - Tasks Overview May 7th 2026
Gorazd Drevenšek
UL MF

## Slide 2: Scope of the WP4: Building the Radiopharmaceutical Pipeline
WP4 builds the complete radiopharmaceutical pipeline that bridges isotope production (WP3) with clinical application readiness. It encompasses five interconnected tasks spanning lab infrastructure, radionuclide selection, ligand development, compound synthesis, and preclinical evaluation
GMP Lab Infrastructure
Radionuclide Identification
Ligand Strategy
Compound Development
Preclinical Evaluation
Safe, radiation-protected LAB conditions for radionuclide production
Clinically relevant isotopes aligned with LINAC feasibility
Targeted molecular design; chelators and carrier molecules
Radiolabelling, synthesis, quality control, stability testing
In vitro / in vivo protocols: imaging, pharmacokinetics
Five Strategic Pillars
Core Objective
Partners involved: BIOKOSMOS SA (GR), UL (SI), DKFZ (DE), AuTh (GR)

## Slide 3: Key Activities - (M1–M18); some completed
Activity | Description | Status
Literature review (T4.1) | Systematic review of radiation protection standards; GMP lab requirements | Completed
Lab specification (T4.1) | Draft specifications for radiation shielding, ventilation, waste management | Completed → D4.1
Radionuclide analysis (T4.2) | Identification of candidate isotopes producible by LINAC with clinical relevance | In progress
Ligand target screening (T4.3) | Initial survey of high-impact molecular targets (PSMA, FAPI, somatostatin) | In progress
Coordination with WP3 | Joint meetings on beam parameters and isotope production feasibility | Ongoing
How it supports IFIGENEIA goals?
WP4 activities directly enable the translation of LINAC-produced isotopes into clinically applicable radiopharmaceuticals, fulfilling IFIGENEIA's mission to establish a regional excellence hub.
Delays / Issues
No critical delays reported. T4.5 starts M19 as planned. Dependency on WP3 beam parameter outputs is being managed through regular joint coordination meetings.

## Slide 4: Scientific & Technical Impact
Relevance for Stakeholders
Hospitals: Access to locally produced diagnostic and therapeutic isotopes (theranostics)
Research: Standardised preclinical protocols for radiopharmaceutical evaluation
Industry: GMP-ready pipeline enabling commercial development
Regulators: Radiation safety framework aligned with EU GMP
Scientific & Technical Contributions
New isotope capability: Identification of ≥5 clinically relevant radionuclides (¹⁷⁷Lu, ⁹⁹ᵐTc, ⁴³Sc, ⁴⁴gSc, ⁴⁷Sc)
Improved ligand targeting: Evaluation of chelator-ligand combinations for PSMA and FAPI targets
Radiation safety: GMP-compliant lab specifications addressing regional infrastructure gaps
Measurable Results to Date
Candidate radionuclide shortlist: 5+ isotopes under evaluation (T4.2)
Lab specification document: D4.1 completed (May 2026)
Radionuclide selection report: D4.2 prepared (May 2026
Ligand target candidates: 3 molecular targets under active evaluation (T4.3)
Lasting Results
Lab specifications, radionuclide selection criteria, and preclinical protocols will remain as open resources for clinics, research centres, and industry partners in the region, ensuring long-term impact.

## Slide 5: Implementation Status by Task
Task | Lead Partner / Presenter | Period | Status | Key Output
T4.1– Lab conditions | BIOKOSMOS SA (Athanasios Zacharakis), GR | M1–M42 | ✅ IMPLEMENTED | D4.1 submitted (May 2026)
T4.2– Radionuclides | UL (Marko Krošelj), SI | M5–M42 | ✅ IMPLEMENTED | D4.2 submitted (May 2026)
T4.3– Ligands | UL (Marko Krošelj), SI | M5–M42 | 🔄 PARTIAL | Ligand target list in progress
T4.4– Compounds | DKFZ (Adela Simkova), DE | M5–M42 | 🔄 PARTIAL | Protocol drafts in development
T4.5– Preclinical | AuTh (Chryssa Bekiari), GR | M18–M48 | ⏳ STARTING M18 | On schedule
Missing Inputs
Final beam parameter data from WP3 is required to complete the radionuclide feasibility ranking (T4.2).
Implementation Overview
Deliverable Contributions |  |  | 
Deliverable | Due | Contribution | Comp.
D4.1 - Lab specs | May 2026 | BIOKOSMOS: shielding, GMP layout | ~95%
D4.2 - Radionuclides | May 2026 | UL: clinical needs + LINAC matrix | ~90%

## Slide 6: Dissemination & Stakeholder Engagement
Hospitals & Clinics
  Access to locally produced diagnostic and therapeutic isotopes.
Research Centres
  Standardised preclinical protocols for evaluation.
Industry (Pharma/Biotech)
  GMP-ready pipeline enabling commercial development.
Regulators
  Radiation safety framework aligned with EU GMP.
Relevance for Stakeholders
Event | Date | Contribution
Kick-off Meeting | M1 | WP4 scope and task plan presented
WP4–WP3 Coordination | M6, M12 | Isotope feasibility & beam parameters
EANM 2025 | 2025 | Radionuclide selection methodology
Regional Workshop | M12 | Lab specification approach presentation
Others? |  | 
Dissemination Activities
No. WP4 monthly meetings | 9
No. Task / subgroups meetings | 2-4
Questionnaire for hospitals meetings | 2

## Slide 7: Proactive Risk Management: Risk Register
Risk Description | Likelihood / Impact | Mitigation Strategy
Delay in isotope availability -Dependency on WP3 beam outputs | Medium / High | Joint WP3–WP4 coordination meetings; parallel literature-based feasibility work to maintain timeline.
Regulatory / GMP compliance -Delays in lab certification | Low / Medium | Early engagement with national radiation protection authorities; alignment with EU GMP standards from the design phase.
Partner capacity constraints -Resource issues at DKFZ or AuTh | Low / Medium | Task leads confirmed; regular progress monitoring; timeline built with internal buffers.
Preclinical facility access -Availability of AuTh facilities for T4.5 | Low / Medium | Facilities pre-identified and secured; protocols being prepared in advance for immediate start at M19.

## Slide 8: June 2026 Milestone: Internal Reporting
Expected Results by June 2026 | Expected Results by June 2026
T4.1 | D4.1 finalised and submitted; radiation protection framework documented
T4.2 | D4.2 finalised; ranked shortlist of ≥5 radionuclides with LINAC feasibility
T4.3 | Ligand target list with preliminary chelator-molecule pairing recommendations
T4.4 | Protocols concepts under development
T4.5 | Preclinical evaluation protocol framework initiated (M19 start)
Planned Deliverables |  | 
Deliverable | Status | Notes
D4.1 - Lab specs | Prepared | Awaiting formal acceptance
D4.2 - Radionuclides | Prepared | Final WP3 data pending
D4.3 – Protocols for pre-clinical ligand-isotope compound. | In preparation | Expected Q3 2026
WP4 is on schedule. The critical May 2026 deliverables (D4.1, D4.2) are prepared. The radiopharmaceutical pipeline is being built systematically, with strong inter-WP coordination and clear pathways to clinical and industrial application

## Slide 9: Thank you for your attention
CONTACT INFORMATION
Gorazd Drevenšek
University of Ljubljana, Faculty of Medicine
Email: gorazd.drevensek@mf.uni-lj.si
Phone: +386 41 561 283